## Cost Overview
Cost Type | Planned Cost | Actual Cost | Variance | Percentage Deviation
Development | 10000 | 9500 | 500 | 5
Marketing | 5000 | 5500 | -500 | -10
Operations | 3000 | 2900 | 100 | 3.33

## Project Overview
Project Name | Start Date | End Date | Status | Completion Percentage
Stock Web App | 01-Jan-2024 | 30-Sep-2024 | In Progress | 75
New Feature X | 01-Feb-2024 | 30-Apr-2024 | Completed | 100

## Resource Overview
Resource Name | Role | Allocated Hours | Worked Hours | Remaining Hours
John Doe | Developer | 200 | 150 | 50
Jane Smith | Marketing Lead | 100 | 80 | 20

## Milestone Report
Milestone | Planned Date | Actual Date | Status | Completion Percentage
Alpha Release | 15-Apr-2024 | 10-Apr-2024 | Completed | 100
Beta Testing | 01-Jun-2024 | 05-Jun-2024 | In Progress | 70

## Task Cost Overview
Task Name | Estimated Cost | Actual Cost | Variance | Task Status
Feature Development | 500 | 450 | 50 | Completed
UI Design | 200 | 250 | -50 | In Progress